## Daily Status
Daily Update
Date | Ajay |  | Dhivya |  | Jambukeshwaran |  | Bala |  | Aishwarya |  | Arasan
| Work Done | Pending | Work Done | Pending | Work Done | Pending | Work Done | Pending | Work Done | Pending | Work Done | Pending
Day1-13/8/2020 | New Connection Component UI | Nil | Login UI | Nil | Tariff UI | Nil | New Connection Component UI | Nil | Login UI | Nil | Tariff UI | Nil
Day2-14/8/2020 | Admin UI-Login,plan,query,Integration,routing | Nil | Home Page UI | Home page | User UI-Main | Nil | Admin UI-Login,plan,query | Nil | Admin UI-Login,plan,query,Integration,routing | Nil | User UI-Main | Nil
Day3-15/8/2020 | Admin UI-History,user control,faq,Integration,routing | Nil | Home page contn,Services | Nil | User Ui-create query,all query | Nil | Admin UI-History,user control,faq,Integration,routing | Nil | Home page contn,Services | Nil | User Ui-create query,all query | Nil
Day4-16/8/2020 | Admin create/Edit plan,Admin Answer Query API,Payment Gateway,Admin-User Control API | New connection API,Admi- User-History | Login & SIGNUP API | Nil | user query UPI,tarif API | ALL billing Api | Admin create/Edit plan,Admin Answer Query API,Payment Gateway,Admin-User Control API | New connection API,Admi- User-History | Login & SIGNUP API | Nil | user query UPI,tarif API | ALL billing Api
Day5-17/8/2020 | API Creation for New connection,Admin-user control,Queries,Generate bill,reminder bill,create/edit plan | API Integration | API for login,signup | Nil | API-Tariff,creation of user queries,Raised queries,user usage API,Bill Payment API,changing plan api,API for changing Payment Status,API to fetch user details,API-User offers,API-get plan type | Nil | API Creation for New connection,Admin-user control,Queries,Generate bill,reminder bill,create/edit plan | API Integration | API for login,signup | Nil | API-Tariff,creation of user queries,Raised queries,user usage API,Bill Payment API,changing plan api,API for changing Payment Status,API to fetch user details,API-User offers,API-get plan type | Nil
Day6-18/8/2020 | API INTEGRATION IN ANGULAR | UI fix | API INTEGRATION IN ANGULAR | UI fix | API INTEGRATION IN ANGULAR | UI fix | API INTEGRATION IN ANGULAR | UI fix | API INTEGRATION IN ANGULAR | UI fix | API INTEGRATION IN ANGULAR | UI fix

## Team Schedule
Task | Days | START DATE | END DATE | Resource Name
Wireframe | 1 | 2020-08-12 | 2020-08-12 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
DB Creation | 1 | 2020-08-13 | 2020-08-13 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu | NOTE
Angular Skeleton | 2 | 2020-08-13 | 2020-08-14 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu | End Time: 11:00 PM IST
Component-Login Page | 2 | 2020-08-13 | 2020-08-14 | Aishwarya,Dhivya
Component-Navbar | 2 | 2020-08-13 | 2020-08-14 | Ajay,Bala
Component-New Connection | 2 | 2020-08-13 | 2020-08-14 | Ajay,Bala
Component-Tariff | 2 | 2020-08-13 | 2020-08-14 | Jambu,Arasan
Component-Tariff | 2 | 2020-08-13 | 2020-08-14 | Jambu,Arasan
Component-User UI -Main(Billing) | 3 | 2020-08-13 | 2020-08-15 | Jambu,Arasan
Component-User UI - Create Qyery | 3 | 2020-08-13 | 2020-08-15 | Jambu,Arasan
Component-User UI - View Query | 3 | 2020-08-13 | 2020-08-15 | Jambu,Arasan
Component-Admin User Control | 3 | 2020-08-13 | 2020-08-15 | Ajay,Bala
Component-Admin User Queries | 3 | 2020-08-13 | 2020-08-15 | Ajay,Bala
Component-Admin History | 3 | 2020-08-13 | 2020-08-15 | Ajay,Bala
Component-Admin Plan | 3 | 2020-08-13 | 2020-08-15 | Ajay,Bala
Component-Home | 3 | 2020-08-13 | 2020-08-15 | Aishwarya,Dhivya
Component-FAQ | 1 | 2020-08-15 | 2020-08-15 | Aishwarya,Dhivya
Component-Services | 2 | 15/08/2020 | 16/08/2020 | Aishwarya,Dhivya
Design sync | 6 | 2020-08-13 | 2020-08-18 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
API Integration | 3 | 2020-08-15 | 2020-08-17 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Dynamic Data Fetching | 3 | 2020-08-16 | 2020-08-18 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Project Overall Setup | 2 | 2020-08-17 | 2020-08-18 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Documentation | 1 | 2020-08-18 | 2020-08-18 | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu

## Progress
Task | Days | START DATE | END DATE | Status | Resource Name
Wireframe | 1 | 2020-08-12 | 2020-08-12 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
DB Creation | 1 | 2020-08-13 | 2020-08-13 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Angular Skeleton | 2 | 2020-08-13 | 2020-08-14 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Component-Login Page | 2 | 2020-08-13 | 2020-08-14 | Completed | Aishwarya,Dhivya
Component-Navbar | 2 | 2020-08-13 | 2020-08-14 | Completed | Ajay,Bala
Component-New Connection | 2 | 2020-08-13 | 2020-08-14 | Completed | Ajay,Bala
Component-Tariff | 2 | 2020-08-13 | 2020-08-14 | Completed | Jambu,Arasan
Component-Tariff | 2 | 2020-08-13 | 2020-08-14 | Completed | Jambu,Arasan
Component-User UI -Main(Billing) | 3 | 2020-08-13 | 2020-08-15 | Completed | Jambu,Arasan
Component-User UI - Create Qyery | 3 | 2020-08-13 | 2020-08-15 | Completed | Jambu,Arasan
Component-User UI - View Query | 3 | 2020-08-13 | 2020-08-15 | Completed | Jambu,Arasan
Component-Admin User Control | 3 | 2020-08-13 | 2020-08-15 | Completed | Ajay,Bala
Component-Admin User Queries | 3 | 2020-08-13 | 2020-08-15 | Completed | Ajay,Bala
Component-Admin History | 3 | 2020-08-13 | 2020-08-15 | Completed | Ajay,Bala
Component-Admin Plan | 3 | 2020-08-13 | 2020-08-15 | Completed | Ajay,Bala
Component-Home | 3 | 2020-08-13 | 2020-08-15 | Completed | Aishwarya,Dhivya
Component-FAQ | 1 | 2020-08-15 | 2020-08-15 | Completed | Aishwarya,Dhivya
Component-Services | 2 | 15/08/2020 | 16/08/2020 | Completed | Aishwarya,Dhivya
Design sync | 6 | 2020-08-13 | 2020-08-18 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
API Integration | 2 | 2020-08-15 | 2020-08-17 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Dynamic Data Fetching | 3 | 2020-08-16 | 2020-08-18 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Project Overall Setup | 2 | 2020-08-17 | 2020-08-18 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu
Documentation | 1 | 2020-08-18 | 2020-08-18 | Completed | Aishwarya,Dhivya,Ajay,Bala,Arasan,Jambu